## Sheet1
Programme Area: Economic Devepment
Sub-Programme: Agriculture Development | [15 empty] | DRAFT COMPOSITE ACTION PLAN FOR 2020
S/N | Activity Description | Location | Output Indicator | Quarterly Time Schedule |  |  |  | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementing Agency | Collaborators
|  |  |  | 1st | 2nd | 3rd | 4th | IGF | GOG | DONORS | TOTAL COST
1 | Organize two (2) budget sessions, four (4) performance review meetings and submit quarterly and annual reports. | Ashaiman | 2 budget sessions, 4 performance review meetings and submit quarterly and annual reports organised. | X | X | X | X |  | 1000 | 15000 | 16000 | DACF, MAG | Agric | MAG, GOG
2 | Pay Office Administrative expenses (Utilities, stationary, equipment repairs, vehicle and motorbike running and maintenance. | Ashaiman | Office Administration undertaken | X | X | X | X |  | 1000 | 3000 | 4000 | DACF, MAG | Agric | ASHMA RAD | 8000
3 | Organize National Farmers’ Day. | Ashaiman | National Farmers’ Day organised. |  |  |  | X |  | 65000 |  | 65000 | DACF | Agric | ASHMA
4 | Organize extension and research activities. | Ashaiman | extension and research activities organised. | X | X | X | X | 9000 | 6000 | 21600 | 36600 | IGF, MAG, DACF | Agric | MAG, GOG, IGF
5 | Construct 1No. Abattoir | IDA | 1No. Abattoir construced | X | X | X | X |  | 800000 |  | 800000 | GOG | Central Adm. | Works
Programme Area: Economic Development
Sub-Programme: Agriculture Development
S/N | Activity Description | Location | Output Indicator | Quarterly Time Schedule |  |  |  | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementing Agency | Collaborators
|  |  |  | 1st | 2nd | 3rd | 4th | IGF | GOG | DONORS | TOTAL COST
6 | Organize two (2) capacity building and six (6) trainings sessions for Agric staff. | Ashaiman | 2 Capacity building and 6 trainings sessions oeganised | X | X | X | X | 3000 | 4000 | 36500 | 43500 | IGF, MAG, DACF | Agric | MAG, GOG, IGF
7 | Running of DCACT Secretatriat. | Ashaiman | Running og DCACT secretatriat carried out | X | X | X | X |  | 2000 | 6000 | 8000 | DACF, MAG | Agric | MAG, GOG
8 | Procure protective clothings, GPS, programable calculators and office equipment (printer, photocopy. Etc) | Ashaiman | Protective clothings, GPS, programable calculators and office equipment (printer, photocopy. Etc) procured |  | X | X |  |  | 21000 | 6500 | 27500 | DACF, MAG | Agric | MAG, GOG, OTHERS
9 | Carry out 1296 home and farm visits and 220 monitoring | Ashaiman | 1296 home and farm visits and 220 monitoring carried out | x | x | x | x |  | 16000 | 35000 | 51000 | DACF, MAG | Agric | MAG, GOG, OTHERS
10 | Carry out vaccinations, surveillance and campaign awareness for rabies disease. | Ashaiman | Vaccinations, surveillance and campaign awareness for rabies disease carried out. | X | X | X | X | 1000 | 2500 | 10700 | 13200 | IGF, MAG, DACF | Agric | MAG, GOG, OTHERS
Programme Area: Economic Development
Sub- Programme: Trade, Tourism and Industry Development
S/N | Activity Description | Location | Output Indicator | Quarterly Time Schedule |  |  |  | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementing Agency | Collaborators
|  |  |  | 1st | 2nd | 3rd | 4th | IGF | GOG | DONORS | TOTAL
11 | Trainning in Business innovation/Fishing skills for 30 males | COTVET Accredited Centre- Ashaiman | 30 master craftmen trained at COTVET |  | X |  |  |  | 6000 |  | 6000 | DACF | NBSSI | COTVET
12 | Trainning 30 women in advance soap manufacturing/ marketing | St. Augustine- Ashaiman | 30 women in trained in advance soap manufacturing/ packaging |  | X |  |  |  | 6000 |  | 6000 | DACF | NBSSI | SWCD, .Local Soap manufacturers
13 | Train 30 people (at least 50% being women) in yoghurt and ice cream production | Municipality wide | 30 people (at least 50% being women) trained in yoghurt and ice cream production |  |  | X |  |  | 6000 |  | 6000 | DACF | NBSSI | Service providers, beneficiaries
14 | Support 5 SMEs to attend National Exhibition and Fair ( at least 2 of them should be females) | Municipality wide | 5 SMEs to attended National Exhibition and Fair |  |  |  | X | 5000 |  |  | 5000 | IGF | NBSSI | MFO
15 | Organise Trade & Industry Committee Meeting | ASHMA Conference hall | Trade & Industry Committee Meeting organised | X | X | X | X |  | 8000 |  | 8000 | DACF | NBSSI
Programme Area: Economic Development
Sub- Programme: Trade, Tourism and Industry Development
| Activity Description | Location | Output Indicator | Quarterly Time Schedule |  |  |  | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementing Agency | Collaborators
|  |  |  | 1st | 2nd | 3rd | 4th | IGF | GOG | DONORS | TOTAL
16 | 5. Provide business counselling services to SMEs in business registration and payment of DOPs ( 30 males and 40 females) | Municipality wide | SMEs provided with business counselling services in business registration and payment of DOPs | X | X | X | X | 8000 |  |  | 8000 | IGF | NBSSI | service providers, MFO, MBO, MISD, Cooperatives
17 | Organize consultative meeting with banks, Ghana Standard Authority and Registral General Department atleast 50% being females | Municipality wide | Consultative meeting with banks, GSA and Registral General Department organised with atleast 50% being women |  |  | X |  | 5000 |  |  | 5000 | IGF | NBSSI | financial institutions, GSA, RGD
18 | Train 30 umemployed youth on facial meke up and décor | Kingscourt Int. Sch. | 30 umemployed youth trainned on facial make up and décor |  |  |  | X |  | 60000 |  | 6000 | DACF | NBSSI
Programme Area: Economic Development
Sub- Programme: Trade, Tourism and Industry Development
S/N | Activity Description | Location | Output Indicator | Quarterly Time Schedule |  |  |  | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementing Agency | Collaborators
|  |  |  | 1st | 2nd | 3rd | 4th | IGF | GOG | DONORS | TOTAL
19 | Organize advance training for 30 women in modern technology in fish processing and marketing | Municipal-wide | Advance training in modern technology in fish processing and marketing organised for 30 women |  |  |  | X |  | 6000 |  | 6000 | DACF | NBSSI | Benefiaciary women
20 | Organize management training for 4 transport Co-operatives’ Executives | Municipal- wide | 4no. transport Co-operatives’ Executives trained |  | X |  |  |  | 5000 |  | 5000 | DACF | Department of Co-operatives (D.O.C) | Transport cooperatives
21 | Organize technical skills training in the areas of Book-keeping for the staff of the various co-operative groups | Municipal- wide | Technical skills training in the areas of Book-keeping organized for the staff of the various co-operative groups |  | X |  |  |  | 10000 |  | 10000 | DACF | Department of Co-operatives(D.O.C) | Transport associations, service providers
Programme Area: Social Development
Sub-Programme: Health and Health Service Delivery
S/N | Activity Description | Location | Output Indicator | Quarterly Time Schedule |  |  |  | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementing Agency | Collaborators
|  |  |  | 1st | 2nd | 3rd | 4th | IGF | GOG | DONORS | TOTAL
22 | Completion of fence wall around 2No. CHPs Compound | Jericho, Tsuibleoo | 2no. CHPS compounds fenced |  | X | X |  |  | 250000 |  | 250000 | DACF | MHD | Works Dept
23 | Completion of a 20 bed capacity isolation ward at the Ashaiman polyclinic | Municipal wide | 20 bed capacity isolation ward at the Ashaiman polyclinic |  | X | X | X |  | 40000 |  | 40000 | DACF | AMHD | Development Partners
24 | Purchase anesthetic machine for Ashaiman Polyclinic | Ashaiman Polyclinic | 1no. anesthetic machine procured and in use | X | [5 empty] | 150000 | 150000 | Rotary Club, Ghana | MHD | Development Partners
25 | Procure furniture and equipment for new male and female wards at the polyclinic and Tsui Bleoo CHPs Compund | Ashaiman polyclinic, Tsui Bleoo CHPs compund | Ashaiman polyclinic and Tsui Bleoo CHPs compund furnished | X |  |  |  |  | 90000 |  | 90000 | DACF | AMHD | Development Partners
26 | Support for lmmunisation Programmes | Municipal-wide | National immunisation Programmes supported | X | X | X | X |  | 40000 |  | 40000 | DACF | AMHD | ASHMA
Programme Area: Social Development
Sub-Programme: Health and Health Service Delivery
S/N | Activity Description | Location | Output Indicator | Quarterly Time Schedule |  |  |  | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementing Agency | Collaborators
|  |  |  | 1st | 2nd | 3rd | 4th | IGF | GOG | DONORS | TOTAL
27 | Organise Public Health Emergency Committee | Municipal wide | Public Health Emergency Committee | X | X | X | X | 10000 |  |  | 10000 | IGF | MHD
28 | Caryout disease surveillance and control and containment activities | Municipal wide | Disease surveillance and control and containment activities carried out | X | X | X | X |  | 10000 |  | 10000 | DACF | MHD
29 | Organise quarterly Municipal Health Oversight Committee Meetings | Municipal-wide | Quarterly Municipal Health Oversight Committee Meetings | X | X | X | X | 10000 |  |  | 10000 | IGF | MHD | Key stakeholders
30 | Undertake mid-year performance review meeting |  | mid-year performance review meeting organised |  | x |  | x |  | 33500 |  | 33500 | DACF | MHD | Dev't partners
31 | Suppot Health Directors' Annual Conference |  | Health Director supported to attend Directors' Annual Conference |  |  | X |  |  | 7000 |  | 7000 | DACF | MHD | Dev't partners
Programme Area: Social Development
Sub-Programme: Health and Health Service Delivery
S/N | Activity Description | Location | Output Indicator | Quarterly Time Schedule |  |  |  | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementing Agency | Collaborators
|  |  |  | 1st | 2nd | 3rd | 4th | IGF | GOG | DONORS | TOTAL
32 | Undertake roll back maleria programme (monitoring , screening and treatment, operational research, data validation and management) | Zonal council level | Roll back maleria programme (monitoring , screening and treatment, operational research, data validation and management) | X | X | X | X |  | 77688.37 |  | 77688.37 | DACF | AMHD | NMCP
33 | Undertake HIV/AIDS programme (support) screening, monitoring, training, data validation etc.) in the municipality | Municipal-wide | No. of HIV/AIDS programme ( screening, monitoring, training, data validation organised | X | X | X | X |  |  | 77688.37 | 77688.37 | MSHARP | AMHD | GAC/NACP
Programme Area: Social Development
Sub-Programme: Education and Development
S/N | Activity Description | Location | Output Indicator | Quarterly Time Schedule |  |  |  | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementing Agency | Collaborators
|  |  |  | 1st | 2nd | 3rd | 4th | IGF | GOG | DONORS | TOTAL
34 | Rehabilitate 2no. Basic Schools Block | Municipal-wide | 2no. Basic Schools Block rehabilitated | X | X | X | X |  | 250000 |  | 250000 | DACF | Works Dept | Municipal Education Directorate
35 | Organize My First Day at School for P1 and KGs in the Municipality | Ashaiman | My First Day at School for P1 and KGs organised |  |  | X |  |  | 25000 |  | 25000 | DACF | GES | ASHMA/GHS
36 | Organize STMIE Clinics | Ashaiman | STMIE Clinics organised |  | X | X |  |  | 17500 |  | 17500 | DACF | GES | AshMA
37 | Organize and participate in Municipal and Regional Cultural Festival of Arts | Ashaiman | Municipal and Regional Cultural Festival of Arts organised |  | X | X |  |  | 15000 |  | 15000 | DACF | GES | Municipal sports Council
38 | Support for BECE | Ashaiman | BECE supported |  | X |  |  |  | 40000 |  | 40000 | DACF | GES | AshMA
39 | Support for best teacher awards | Ashaiman | Best teacher awards programme supported |  |  |  | X |  | 20000 |  | 20000 | DACF |  | AshMA
40 | Organise Municipal Education Oversight Committee meeting | Ashaiman | Municipal Education Oversight Committee meeting organised | X | X | X | X | 6000 |  |  | 6000 | IGF | GES | Stakeholders
Programme Area: Social Development
Sub-Programme: Education and Development
S/N | Activity Description | Location | Output Indicator | Quarterly Time Schedule |  |  |  | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementing Agency | Collaborators
|  |  |  | 1st | 2nd | 3rd | 4th | IGF | GOG | DONORS | TOTAL COST
41 | Completion of fence wall around ASHMA No.4 Basic School | Comm. 22 | Fence wall around ASHMA No.4 Basic School completed | X |  |  |  |  | 200000 |  | 200000 | DACF | GES | ASHMA
42 | Supply 100 specialised table with 500 chairs for KGs and 300 dual desk for basic sch. | Municipal-wide | 100 specialised table with 500 chairs for KGs and 300 dual desk for Basic Schools |  | X | X |  |  | 170000 |  | 170000 | DACF | GES | Procurement Unit
43 | Education fund | Municipal-wide | No. of beneficiaries | X | X | X | X |  | 155376.75 |  | 155376.75 | DACF | GES | Fund Implementation Commiittee | 310753.5
44 | Organise Municipal SPAM | Ashaiman | Municipal SPAM org'sed |  |  |  |  | 5000 |  |  | 5000 | IGF | GES | AshMa
Programme Area: Social Development
Sub-Programme: Education and Development
S/N | Activity Description | Location | Output Indicator | Quarterly Time Schedule |  |  |  | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementing Agency | Collaborators
|  |  |  | 1st | 2nd | 3rd | 4th | IGF | GOG | DONORS | TOTAL
45 | Awareness creation on Functional literacy/ JHS and SHS remedial classes | Lebanon Z1-Z5,Jericho, Ashaiman Township,Ash-Newtown,Middle East, Official Town, Roman Down, Tulaku, Adakordzi. | Awareness created on Functional literacy/ JHS and SHS remedial classes | x |  |  |  |  | 5000 |  | 5000 | DACF | Non-Formal Division | ASHMA
46 | Establishment of 30 English classes 2 local language classes |  | 30 English classes 2 local language classes established |  | x |  |  | 2000 |  |  | 2000 | IGF | Non-Formal Division | GES/Community Development
47 | Undertake Quarterly Monitoring and Evaluation of Non-formal Education | Municipal-Wide | Quarterly Monitoring and Evaluation of Non-formal Education undertaken | x | x | x | x |  | 3000 |  | 3000 | DACF | Non-Formal Division | ASHMA
Programme Area: Social Development
Sub-Programme: Education and Development (Sports)
S/N | Activity Description | Location | Output Indicator | Quarterly Time Schedule |  |  |  | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementing Agency | Collaborators
|  |  |  | 1st | 2nd | 3rd | 4th | IGF | GOG | DONORS | TOTAL
48 | Establish data base for all sports clubs in the Municipality | Municipal Wide | Data base for all sports clubs in the Municipality established | X | X | X | X | 2000 |  |  | 2000 | IGF | Sports Unit | Ashma
49 | Organise Municipal sports tournaments for selected teams | Municipal Wide | Municipal sports tournaments for selected teams organised | X | X | X | X | 8000 |  |  | 8000 | IGF | Sports Unit | Ashma
50 | Undertake regional sports festival | Municipal Wide | Regional sports festival undertaken | X | X | X | X |  | 5000 |  | 5000 | DACF | Sports Unit | Ashma
Programme Area: Social Development
Sub-Programme: Social Welfare and Community Development
S/N | Activity Description | Location | Output Indicator | Quarterly Time Schedule |  |  |  | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementing Agency | Collaborators
|  |  |  | 1st | 2nd | 3rd | 4th | IGF | GOG | DONORS | TOTAL
51 | Undertake child non maintainace cases, family reconcilation/counselling | Ashaiman | Child non maintainace cases, family reconcilation/counselling undertaken | x | x | x | x |  | 4000 |  | 4000 | DACF | SWCD | Family heads/opinion leaders
52 | Monitor the utilization of 3% of the DACF given to PWDs and other programmes | Municipal-wide | the utilisation of 3% DACF given to PWDS and other programmes monitored | X | X | X | X |  | 4500 |  | 4500 | Disability Common Fund | DSW | Disability committee
53 | Monitor LEAP payment bi-monthly | Ashaiman | LEAP payment bi-monthly monitered | x | x | x | x |  | 5000 |  | 5000 | DACF | SWCD | Central Adm Banks
54 | Undertake Juvenile Justice Administration | Ashaiman | Juvenile justice administartion carried out | x | x | x | x |  | 6000 |  | 6000 | DACF | SWCD | Police, Judicial Service
55 | Reintegration of missing/abandoned Children with families | Ashaiman | Missing/abandoned children reintegrated with families | x | x | x | x |  | 7000 |  | 7000 | DACF | SWCD | NGOs/SOS
56 | Celebrate World Day Against Child Labour | Ashaiman Municipality | World day against child labour celebrated |  |  | X |  |  | 3408 |  | 3408 | DACF | DSW | School pupils
Programme Area: Social Development
Sub-Programme: Social Welfare and Community Development
S/N | Activity Description | Location | Output Indicator | Quarterly Time Schedule |  |  |  | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementing Agency | Collaborators
|  |  |  | 1st | 2nd | 3rd | 4th | IGF | GOG | DONORS | TOTAL COST
57 | Inspection of early childhood centers/registration | Ashaiman | Early childhood centres/registration inspected | x | x | x | x |  | 4000 |  | 4000 | DACF | SWCD | GES/Environmental Health
58 | Organise eight (8) mass meetings, Home Visits and Demonstrations for 850 participants. (800 women and 50 men). | Selected Electoral Areas | 8No. mass meetings, Home Visits and Demonstrations for 850 participants (800 women and 50 men) organised | x | x | x | x |  |  | 10000 | 10000 | Donors | SWCD | Global Health Alliance Network, Zoomlion
59 | Organise two (2) Workshops on Skills Training and Extension Services for 600 participants. (550 women and 50 men). | Selected Electoral Areas | 2No. Workshops on Skills Training and Extension Services for 600 participants. (550 women and 50 men) organised |  | X | X |  | 3500 | 3500 | 3000 | 10000 | DACF, IGF & Donors | SWCD | NBSSI
Programme Area: Social Development
Sub-Programme: Social Welfare and Community Development
S/N | Activity Description | Location | Output Indicator | Quarterly Time Schedule |  |  |  | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementing Agency | Collaborators
|  |  |  | 1st | 2nd | 3rd | 4th | IGF | GOG | DONORS | TOTAL COST
60 | Organise income generating activities such as Soap and Bead making for 600 participants (550 women and 50 men). | Selected Electoral Areas | income generating activities such as Soap and Bead making for 600 participants. ( 550 women and 50 men). |  | x | x | x |  | 10000 |  | 10000 | DACF | SWCD | ASHMA, NBSSI
Programme Area: Social Development
Sub-Programme:Water and Sanitation
S/N | Activity Description | Location | Output Indicator | Quarterly Time Schedule |  |  |  | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementing Agency | Collaborators
|  |  |  | 1st | 2nd | 3rd | 4th | IGF | GOG | DONORS | TOTAL COST
61 | Desilt drainsand sweeping streets in the Municipality | Traffic Light- Presby Down | Traffic Light- Presby Down drains desilted | X | X |  |  |  | 100000 |  | 100000 | DACF | MEHU | MFO
62 | Procure cleaning materials for Assembly | Ashaiman | cleaning materials for Assembly procured | X | X | X |  |  | 20000 |  | 20000 | DACF | MEHU | MFO, procurement officer
63 | Conduct routine maintenance of sewer lines | Ashaiman low cost | Routine maintenance of sewer lines carried out | X | X | X | X | 10000 |  |  | 10000 | IGF | MEHU | Tema Metropolitan Assembly
64 | Organize 12 monthly clean-up exercise | Ashaiman | 12 monthly clean up exercise organised | X | X | X | X | 106000 | 84000 |  | 190000 | IGF, DACF | MEHU | MFO
65 | Conduct medical screening of 4500 food vendors | Municipal- wide | 4500 food screened |  |  | X | X | 5000 |  |  | 5000 | IGF | MEHU | Food vendors
66 | Prosecute sanitary offenders | Municipal- wide | No. of sanitory offeders prosecuted | X | X | X | X | 6000 |  |  | 6000 | IGF | MEHU | Police
67 | Organise 3 public education on environmental health promotion | Municipal wide | 4 public education on health promotion organised | X | X | X | X | 10000 |  | - |  | - | MEHU | Opinion leaders
68 | Bury unclaimed paupers | Ashaiman | unclaimed pauers buried | X | X | X | X | 5000 |  |  | 5000 | IGF | MEHU | Police
Programme Area: Social Development
Sub-Programme:Water and Sanitation
S/N | Activity Description | Location | Output Indicator | Quarterly Time Schedule |  |  |  | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementing Agency | Collaborators
|  |  |  | 1st | 2nd | 3rd | 4th | IGF | GOG | DONORS | TOTAL COST
69 | Construct a sewer system | New town -TDC Quarters | Sewer system constructed | X | X | X | X |  |  |  |  | GAMA | Project Co-ordinator | MEHU
70 | Procure working tools and materials for sanitation management | ASHMA | Working tools and materials for sanitation management procured | X | X | X | X |  | 25000 |  | 25000 | DACF | MEHU | MFO, procurement officer
71 | Facilitate the construction of 300 household toilet | Ashaiman | Construction of 300 household toilet facilitated | X | X | X | X |  |  |  |  | GAMA | Project Co-ordinator | MEHU
72 | Conduct fumigation exercises | Municipal wide | Fumigation exercise conducted | X | X | X | X | 10000 | 20000 |  | 30000 | IGF DACF | MEHU | Zoomlion,
73 | Organise 4No. evacuation of solid wate at unauthorised areas | Municipal wide | 2No. evacuation of solid wate at unauthorised areas organised | x | x | x | x | 15000 | 20000 |  | 35000 | IGF DACF | MEHU | Zoomlion,
74 | GAMA operational expenses | Municipal-wide | Amount spent | X | X | X | X |  |  | 100000 | 100000 |  | Project Co-ordinator | Project implementing Team
75 | Construct and mechanise 5No. Instituitional Boreholes | Selected Schools | 5No. Instituitional Boreholes constructed and mechanised | X | X |  |  |  | 125000 |  | 125000 | DACF | ASHMA | GES
Programme Area: Environment Infrastructure and Human Settlements
Sub- Programme: Infratructure Development
S/N | Activity Description | Location | Output Indicator | Quarterly Time Schedule |  |  |  | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementing Agency | Collaborators
|  |  |  | 1st | 2nd | 3rd | 4th | IGF | GOG | DONORS | TOTAL COST
76 | Grading and gravelling of selected roads | Municipal-wide | Grading and gravelling of selected roads carried out | X | X | X |  |  | 400000 |  | 400000 | DACF | Urban Roads | beneficiary communities
77 | Construction of drains on selected roads | Municipal wide | dains on selected roads constructed | X | X | X | X |  |  | 4000000 | 4000000 | GAMA
78 | Rehabilitate Kofi Nimo Street / Tema International Sch. Roads | Tema International | Kofi Nimo street/Tema international roads rehabilitated | X | X | X | X |  | 2500000 |  | 2500000 | GOG | Urban Roads | beneficiary communities
79 | Rehabilitate School Road, Channel 11 Road, Ecuado Road Danquah Road (3.2km) | Lebanon | School Road, Channel 11 Road, Ecuado Road Danquah Road (3.2km) rehabilitated | X | X | X | X |  | 6862179.44 |  | 6862179.44 | GOG | Urban Roads | beneficiary communities
80 | Desilting of drains | Municipal wide | Drains disilted | X | X | X | X | 100000 | 100000 |  | 200000 | IGF, DACF | Urban Roads | beneficiary communities
Programme Area: Environment Infrastructure and Human Settlements
Sub- Programme: Infratructure Development
S/N | Activity Description | Location | Output Indicator | Quarterly Time Schedule |  |  |  | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementing Agency | Collaborators
|  |  |  | 1st | 2nd | 3rd | 4th | IGF | GOG | DONORS | TOTAL COST
81 | Construct 5no. Pipe culvert at selected locations | Municipal-wide | 5no. Pipe culvert at selected locations constructed | X | X | X | X | 150000 |  |  | 150000 | IGF | Urban Roads | beneficiary communities
82 | Construct selected drains within Lebanon Zone-1 to Zone 5 | Lebanon Zone-1 to Zone 5 | Selected rains within Lebanon Zone-1 to Zone 5 constructed | X | X | X | X |  | 666524.54 |  | 666524.54 | DPAT Fund | Urban Roads | beneficiary communities
83 | Traffic Management and Safety | Municipal wide | No. of speed humps contructed | X | X | X | X | 100000 |  |  | 100000 | IGF | Urban Roads | beneficiary communities
Programme Area: Environment Infrastructure and Human Settlements
Sub- Programme: Physical Planning
S/N | Activity Description | Location | Output Indicator | Quarterly Time Schedule |  |  |  | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementing Agency | Collaborators
|  |  |  | 1st | 2nd | 3rd | 4th | IGF | GOG | DONORS | TOTAL COST
84 | Secure documents on Assembly lands | ASHMA | Documents for all ASHMA lands acquired | X | X | X | X |  | 50000 |  | 50000 | DACF | Works department | TDC
85 | Organise 4No. SAT meetings | ASHMA | 4No. SAT meetings organised | X | X | X | X |  | 12000 |  | 12000 | DACF | PPD | Planning,
86 | Organise 6No. Spatial Planning Committee, 12No. Technical Committee meetings | ASHMA | 6No. Spatial Planning Committee, 12No. Technical Committee meeting organised | X | X | X | X |  | 48000 |  | 48000 | DACF | PPD | PPD, TDC and others
87 | Organise sensitisation workshop on permiting process | Municipal wide | sensitisation workshop on permiting process organised | X | X |  |  |  | 10000 |  | 10000 | DACF | PPD | PPD, TDC,EPA,ETC.
88 | Preparation of structure plan and local plans for selected communities | middle east, official town, labanon | structure plan and local plans for selected communities prepared |  | X | X | X |  | 45000 |  | 45000 | DACF | PPD | PPD, MWD,MPCU, TDC
Programme Area: Environment Infrastructure and Human Settlements
Sub- Programme: Disaster Prevention and Management
S/N | Activity Description | Location | Output Indicator | Quarterly Time Schedule |  |  |  | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementing Agency | Collaborators
|  |  |  | 1st | 2nd | 3rd | 4th | IGF | GOG | DONORS | TOTAL COST
89 | Undertake Vulnerability and risk assessments | Municipal-wide | Vulnerability and risk assessments undertaken | X | X | X |  |  | 7860 |  | 7860 | DACF | NADMO | Central Admin, ISD, GES, Security Services, Religious Bodies, GHS, Opinion/Traditional Leaders, GNFS, NCCE
90 | Organise quarterly public education on disaster prevention and management | Municipal-wide | Public education on disaster prevention and management organised | X | X | X | X |  | 16000 |  | 16000 | DACF | NADMO
91 | Identify and Map out Hazard areas | Municipal-wide | Hazard areas identified and mapped out | X | X |  |  | 4000 |  |  | 4000 | IGF | NADMO
92 | Organise mid-year and annual performance review neetings with stakeholders: DMC(15), HOD(6), ZC/ZS(14) | Municipal-wide | Mid-year and annual performance review neetings with stakeholders: DMC(15), HOD(6), ZC/ZS(14) organised |  |  | X |  |  | 5000 |  | 5000 | DACF | NADMO
93 | Greening City | Municipal-wide | No. od trees planted and maintained | X | X | X | X |  | 25000 |  | 25000 | DACF | NADMO
94 | Dredging of Gbemi river basins | ASHMA | Gbemi river dredged | X | X |  |  |  | 100000 |  | 100000 | DACF | NADMO
Programme Area: Environment Infrastructure and Human Settlements
Sub- Programme: Disaster Prevention and Management
S/N | Activity Description | Location | Output Indicator | Quarterly Time Schedule |  |  |  | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementing Agency | Collaborators
|  |  |  | 1st | 2nd | 3rd | 4th | IGF | GOG | DONORS
95 | Train Disaster Volunteer Clubs in Schools (50) and Disaster Volunteer Groups(50) | Municipal-wide | Disaster Volunteer Clubs in Schools (50) and Disaster Volunteer Groups(50) trained | X | X | X | X |  | 4000 |  | 4000 | DACF | NADMO | Central Admin, ISD, GES, Security Services, Religious Bodies, GHS, Opinion/Traditional Leaders, GNFS, NCCE
96 | Organise International Day for Disaster Risk Reduction (IDDR) Celebration(13th October) | Municipal-wide | International Day for Disaster Risk Reduction (IDDR) Celebrated |  |  | X |  | 8000 |  |  | 8000 | IGF | NADMO
Programme Area: Governace, Corruption and Adminstration
Sub-Programme: Civil Society and Civic Engagement
S/N | Activity Description | Location | Output Indicator | Quarterly Time Schedule |  |  |  | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementing Agency | Collaborators
|  |  |  | 1st | 2nd | 3rd | 4th | IGF | GOG | DONORS | TOTAL COST
97 | Create Community level awareness on the importance of citizens active involvement in local governance and peaceful election | Municipal-wide | Community level awareness creaed on the importance of citizens active involvement in local governance |  | X | X | X | 20000 |  |  | 20000 | IGF | NCCE | EC
98 | Sensitize communities in 17 electoral areas on their Civil rights | Selected Electoral Areas | 17 electoral areas sensitsed on their Civil rights | X | X | X | X |  | 5000 |  | 5000 | DACF | Comm. Development Unit | NCCE
99 | Organise Sensitization Program for 150 women on domestic voilence against women and early child marriage | municipal wide | Sensitization Program on domestics voilence against women and early chilld marriage | X | X | X | X |  | 10000 |  | 10000 | DACF | Gender Dest officer | NCCE, Ashma
100 | Organise 4 Town Hall meetings | Municipal-wide | 4Town Hall meetings organised | X | X | X | X |  | 98000 |  | 98000 | DACF | Central Admin | General public
101 | Quarterly MCE's visit to electoral areas | 17 Electoral Areas | MCE's visit electoral areas carried out | X | X | X | X |  | 51000 |  | 51000 | DACF | Cectral Admin | General public
102 | Organise public education on the functions of the Assembly | Municipal-wide | Public education on the functions of the Assembly organised | X | X | X | X | 24000 |  |  | 24000 | IGF | PRCC | General public
Programme Area: Governace, Corruption and Adminstration
Sub-Programme: Management and Adminstration
S/N | Activity Description | Location | Output Indicator | Quarterly Time Schedule |  |  |  | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementing Agency | Collaborators
|  |  |  | 1st | 2nd | 3rd | 4th | IGF | GOG | DONORS | TOTAL
103 | Provide 2-day training on LGS Protocols | Central Administration | 2-day training on staffing norms and human resource policy organised | X |  |  |  |  | 12000 |  | 12000 | DACF | HR | HoDs and Management
104 | Pay Stafff welfare and medical expenses | Central Administration | Amount of funds spent | X | X | X | X | 63000 |  |  | 63000 | IGF | ASHMA | Heads of Depts/Units
105 | Organise seminars/ conference/ worshops/ meetings | Central Administration | Seminars/conference/worshops/meeting attended | X | X | X | X | 233500 |  |  | 233500 | IGF | ASHMA | Heads of Depts/Units
106 | Pay Library and subscription, postal charges | Central Administration | Amount of funds spent | X | X | X | X | 15000 |  |  | 15000 | IGF | ASHMA | Heads of Depts/Units
107 | Pay Donations | Central Administration | Amount of funds spent | X | X | X | X | 80000 |  |  | 80000 | IGF | ASHMA | Heads of Depts/Units
108 | Best worker awards and rewards | Central Administration | Best worker awards and rewards organised | X | X | X | X | 50000 |  |  | 50000 | IGF | Cental Admin | Heads of Depts/Units
109 | Pay salaries of casual labourers | Central Administration | Salaries of casual labourers paid | X | X | X | X | 929291.01 |  |  | 929291.01 | IGF | Budget Unit | Finance Dept.
110 | Pay hotel Accommodation | Central Administration | Hotel accommodation expenses paid | X | X | X | X | 50000 |  |  | 50000 | IGF | Budget Unit | Finance Dept.
Programme Area: Governace, Corruption and Adminstration
Sub-Programme: Management and Adminstration
S/N | Activity Description | Location | Output Indicator | Quarterly Time Schedule |  |  |  | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementing Agency | Collaborators
|  |  |  | 1st | 2nd | 3rd | 4th | IGF | GOG | DONORS | TOTAL COST
111 | Pay allawances for offical Assignment (Honorarium, out of station allowance, T&T) | Central Administration | Alawances for offical Assignment paid | X | X | X | X | 597000 |  |  | 597000 | IGF | Budget Unit | Finance Dept.
112 | Support Traditional Council | Central Administration | Traditional Council supported | X | X | X | X | 20000 |  |  | 20000 | IGF | Budget Unit | Finance Dept.
113 | Maitenance of official vehicle | Central Administration | Official vehicle maintained | X | X | X | X | 450000 |  |  | 450000 | IGF | Central Admin | HoDs
114 | Procure fuel and lubricants for official vehicles | Central Administration | Fuel and lubricants procured for official vehicles | X | X | X | X | 300000 |  |  | 300000 | IGF | Central Admin | Finance Dept.
115 | Rental of vehicles | Central Administration | Amount of funds spent | X | X | X | X | 20000 |  |  | 20000 | IGF | Budget Unit | Finance Dept.
116 | Printed Materials and Stationery | Central Administration | Printed Materials and Stationery expense paid | X | X | X | X | 400000 |  |  | 400000 | IGF | Budget Unit | Finance Dept.
117 | Foreign Travel cost and expenses | Central Administration | Amount of funds spent | X | X | X | X | 50000 |  |  | 50000 | IGF | ASHMA | Finance Dept.
118 | Local Travel cost and expenses | Central Administration | Amount of funds spent | X | X | X | X | 50000 |  |  | 50000 | IGF | ASHMA | Finance Dept.
Programme Area: Governace, Corruption and Adminstration
Sub-Programme: Management and Adminstration
S/N | Activity Description | Location | Output Indicator | Quarterly Time Schedule |  |  |  | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementing Agency | Collaborators
|  |  |  | 1st | 2nd | 3rd | 4th | IGF | GOG | DONORS | TOTAL COST
119 | Maintenace of furniture and Fixtures | Central Administration | Furniture and Fixture maintained | X | X | X | X | 30000 |  |  | 30000 | IGF | Works Dept | Budget
120 | Maintenace of General Equipment/ plant | Central Administration | General Equipment/ plant maintained | X | X | X | X | 23000 |  |  | 23000 | IGF | Works Dept | Budget
121 | Procure office facilities, supplies and accessories | Central Administration | Quantities of items procured | X | X | X | X |  | 200000 |  | 200000 | DACF | Procurement Unit | Budget
122 | Pay utility Charges | Central Administration | Utility charges paid | X | X | X | X | 214000 |  |  | 214000 | IGF | Finance Dept. | Central Admin
123 | Complete the construction of Admin Block B | Central Administration | construction of Admin Block B completed |  | X |  |  |  | 20000 |  | 20000 | DACF | HR | Finance
124 | Undertake Operational enhancement expenses | Central Administration | Operational enhancement expenses undertaken | X | X | X | X | 120000 |  |  | 120000 | IGF | Procurement Unit | Finance-Dept
125 | Official celebrations/ceremonial functions, state protocol service/ end of year | Municipal-wide | Official celebrations/ceremonial functions, state protocol service/ end of year organised | X | X | X | X | 80000 |  |  | 80000 | IGF | ISD | Community Devt
126 | Payment of Transfer Grants | Central Administration | Transfer Grants paid |  | X | X |  |  | 100000 |  | 100000 | DACF | Budget Units | MPCU, Assembly members
Programme Area: Governace, Corruption and Adminstration
Sub-Programme: Management and Adminstration
S/N | Activity Description | Location | Output Indicator | Quarterly Time Schedule |  |  |  | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementing Agency | Collaborators
|  |  |  | 1st | 2nd | 3rd | 4th | IGF | GOG | DONORS | TOTAL COST
127 | Pay bank Charges | Central Administration | bank Charges paid |  |  | X | X |  | 75000 |  | 75000 | DACF | Budget Unit | MPCU, Assembly members, trade Associations
128 | Organise education on Payment of Taxes and Rates for 60 youth groups, churches and Mosques | Municipal-wide | education on Payment of Taxes and Rates for 60 youth groups, churches and Mosques | X | X | X | X | 8000 |  |  | 8000 | IGF | ISD | Community Devt
129 | Prepare and gazette 2021 FFR | Central Administration | FFR prepared and gazetted |  |  | X | X |  | 70000 |  | 70000 | DACF | Budget Unit | MPCU, Assembly members, stakeholders
130 | Prepare 2021 composite AAP and Budget | Central Administration | 2021 composite Budget prepared |  | X | X |  |  | 120000 |  | 120000 | DACF | Planning and Budget Units | MPCU, Assembly members
131 | Sponsor 3 middle mgt staff to attend ILGS Maters Degree programme | Central Administration | 3 middle mgt staff to attend ILGS Maters Degree programme sponsored |  |  | X |  |  |  |  | 30000 | DACF | HR | Middle staff mgt
Programme Area: Governace, Corruption and Adminstration
Sub-Programme: Management and Adminstration
S/N | Activity Description | Location | Output Indicator | Quarterly Time Schedule |  |  |  | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementing Agency | Collaborators
|  |  |  | 1st | 2nd | 3rd | 4th | IGF | GOG | DONORS | TOTAL COST
132 | Organise orientation for 2020-2021 national service personel | Central Administration | orientation for 2020-2021 national service personel organised |  |  | x |  | 5000 |  |  | 5000 | IGF | HR | Units/dept heads
133 | Sponsor 3 staff for continuous professional development (Finance & Audit, MCD) | ASHMA | 3 staff sponored for continuous professional development (Finance & Audit) |  | X | X | X |  | 20000 |  | 20000 | DACF | HR | ICAG
134 | Prepare and submit internal audit report | ASHMA | Audit reports prepared and submitted to relevant stakeholders | X | X | X | X | 20000 |  |  | 20000 | IGF | Internal Audit Unit
135 | Serminars/conferences/workshops/meetings expenses-management, budget committee, MPCU, MEOC, entity tender committees, Audit committee, NHOC and other technical committee meetings | Central Administration | Serminars/conferences/workshops/meetings organised | X | X | X | X | 60000 |  |  | 60000 | IGF | ASHMA | Planning, Budget Unit and HODs
Programme Area: Governace, Corruption and Adminstration
Sub-Programme: Management and Adminstration
S/N | Activity Description | Location | Output Indicator | Quarterly Time Schedule |  |  |  | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementing Agency | Collaborators
|  |  |  | 1st | 2nd | 3rd | 4th | IGF | GOG | DONORS | TOTAL COST
136 | Pay External consultants | central Administration | Exeternal consultants paid | X | X | X | X | 30000 |  |  | 30000 | IGF | ASHMA | external consultants
137 | Counterpart fund (Construction of Artisana Village) | IDA | Artisana Village constructed | X | X | X | X |  | 150000 |  | 150000 | DACF | ASHMA | Partners
138 | Serminars/conferences/workshops (local)- AAP, Plan reviews, Monitoring and Evaluation including elections, Budget reviews, Budget dissermination, Budget hearings and Social Accountability forum | central Administration | AAP, Plan reviews, Monitoring and Evaluation including elections, Budget reviews, Budget dissermination, Budget hearings and Social Accountability forum held | X | X | X | X |  | 150000 |  | 150000 | DACF | MPCU | Budget Unit
Programme Area: Governace, Corruption and Adminstration
Sub-Programme: Democratic Governance
S/N | Activity Description | Location | Output Indicator | Quarterly Time Schedule |  |  |  | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementing Agency | Collaborators
|  |  |  | 1st | 2nd | 3rd | 4th | IGF | GOG | DONORS | TOTAL
139 | Completion of fence wall and land scapping of MCE residence (work-in-progress) | Comm-22 | Fence wall and land scapping of MCE residence completed | X | X |  |  | 100000 | 350000 |  | 450000 | IGF, DACF | Finance Dept | Budget Unit, Works Dept
140 | Furnishing of MCE official residence | Ashaiman | MCE's official recidence furnished |  | X |  |  |  | 250000 |  | 250000 | DACF | Procurent Unit | Works Dept.
141 | Board/Committees/Commission Allawance/ General Assembly | Central Administration | General Assembly and sub-committees' meetings organised | X | X | X | X | 590000 |  |  | 590000 | IGF | Budget Unit | Assembly members and Heads of Depts
142 | Support to lower Structure | Municipal-wide | Level of functionality of the lower structures | X | X | X | X |  | 155376.75 |  | 155376.75 | DACF | Central Admin | Finance Dept
143 | Pay Assembly members mobilization | Municipal-wide | Assembly members mobilization paid | X | X | X | X | 210000 |  |  | 210000 | IGF | Finance Dept | Budget Unit
144 | Pay for community engagement by Assembly members | Municipal-wide | Community engagement to Assembers paid | X | X | X | X | 142800 |  |  | 142800 | IGF | Finance Dept | Budget Unit
145 | Support to community innited projects | Municipal-wide | Community engagements supported | X | X | X | X |  | 338441.74 |  | 338441.74 | DACF | ASHMA | Budget
Programme Area: Governace, Corruption and Adminstration
Sub-Programme: Democratic Governance
S/N | Activity Description | Location | Output Indicator | Quarterly Time Schedule |  |  |  | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementing Agency | Collaborators
|  |  |  | 1st | 2nd | 3rd | 4th | IGF | GOG | DONORS | TOTAL
146 | Support to security services | Central Administration | Security services supported in their operations | x | x | x | x |  | 150000 |  | 150000 | DACF | ASHMA | Central Admin
147 | Monitoring and evaluation of Assembly programmes and projects | Municipal-wide | Assembly programmes and projects monitored | X | X | X | X |  | 120000 |  | 120000 | DACF | Planning Unit | MPCU members
148 | Train Assembly members on budget and plan preparation, Local Governance System | Central Administration | Assembly members trained in Local Governance System; Plan and budget preparation |  |  | X |  |  | 20000 |  | 20000 | DACF | HR | Management
149 | Train women in lobbying and advocacy skills | Municipal-wide | No. of women trainning |  | X | X |  | 2000 |  | 10000 | 12000 | GIZ, IGF | Planning Uni | Delopment partners
150 | Organise training programme for the taskforce of the Assembly | Central Administration | Law enforcement unit of the Assembly trained |  | X |  |  |  | 10000 |  | 10000 | DACF | HR | Security Services and Management
151 | Rehabilitate and install new streetlights | Municipal-wide | Streetlights maintained | X | X | X | X | 120000 | 345000 |  | 465000 | DACF, IGF | Works Dept | Assembly members
152 | Election support | Municipal-wide | Election supported | X | X | X | X | 250000 | 250000 |  | 500000 | IGF, DACF | Central Admin | EC
Programme Area: Management and Administration
Sub- Programme: Human Security and Public Safety
S/N | Activity Description | Location | Output Indicator | Quarterly Time Schedule |  |  |  | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementing Agency | Collaborators
|  |  |  | 1st | 2nd | 3rd | 4th | IGF | GOG | DONORS | TOTAL
153 | Organise 2 No. capacity programmes for transport operators and other stakeholders in Ashaiman | muncipal wide | 2No. capacity programmes for transport operators and other stakeholders in Ashaiman organized | x |  | x |  | 3000 |  |  | 3000 | IGF | UPTU | GPS
154 | Organise two (2) stakeholder meetings to facilitate institutional collaboration between the enforcement unit of the Assembly and other enforcement agencies |  | Two (2) stakeholder meetings to facilitate institutional collaboration between the enforcement unit of the Assembly and other enforcement agencies organised |  |  |  |  | 5000 |  |  | 5000 | IGF | UPTU | Institute of Transport, MFO
155 | Train 2 UPTU staffs in Transport planning | Accra | 2 UPTU staffs trained in Transport planning |  |  | X |  | 5000 |  |  | 5000 | IGF | UPTU | transport operators
156 | Update Passenger Transport Database | muncipal wide | Passenger Transport Database updated | X | X | X | X | 4000 |  |  | 4000 | IGF | Assembly | UPTU staff
157 | Regulate activities of vehicle terminals | muncipal wide | Activities of vehicle terminals regulated | X | X | X | X | 1000 |  |  | 1000 | IGF | Assembly | UPTU staff
Programme Area: Governace, Corruption and Adminstration
Sub-Programme: Finance and Revenue Administration
S/N | Activity Description | Location | Output Indicator | Quarterly Time Schedule |  |  |  | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementing Agency | Collaborators
|  |  |  | 1st | 2nd | 3rd | 4th | IGF | GOG | DONORS | TOTAL
158 | Train Revenue collectors/ Data billing personnel | ASHMA | Revenue collectors/ Data billing personnel trainned | X |  | X |  | 49000 |  |  | 49000 | IGF | Finance Unit | Human resource/ BUDGET
159 | Educate rate payers on the need to pay rates promptly | ASHMA | Rate payers educated on the need to pay rates promptly |  |  |  |  | 80000 |  |  | 80000 | IGF | Finance Unit | Budget
160 | Undertake Monitoring and supervision of Revenue mobilization activities | Ashaiman | Monitoring and supervision of Revenue mobilization activities carried out | X | X | X | X | 20000 |  |  | 20000 | IGF | Finance | Budget
161 | Construct 2No.pay point at market sequence | Ashaiman | 2No.pay point at market sequence constructed |  | x | x |  | 40000 |  |  | 40000 | IGF | Works | Finance
162 | Purchase value books | ASHMA | Value books purchased | x | x | x | x | 100000 |  |  | 100000 | IGF | Finance | Finance
163 | Pay allawaces for Revenue Mobilisation mob-up | Ashaiman | Allawaces for Mobilisation mob-up paid |  |  | x | x | 84000 |  |  | 84000 | IGF | Finance | Budget
Programme Area: Governace, Corruption and Adminstration
Sub-Programme: Finance and Revenue Administration
S/N | Activity Description | Location | Output Indicator | Quarterly Time Schedule |  |  |  | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementing Agency | Collaborators
|  |  |  | 1st | 2nd | 3rd | 4th | IGF | GOG | DONORS | TOTAL
164 | Undertake Property Evaluation and Validation | ASHMA | Property Evaluation and Validation carried out |  | X | X |  | 150000 |  |  | 150000 |  | Finance | Budget/Audit
165 | Organize Revenue performance review | ASHMA | Revenue performance review organised | X | X | X | X | 8600 |  |  | 8600 | IGF | Finance
166 | Prepare monthly and annual accounts | ASHMA | Monthly and annual accounts prepared and distributed | X | X | X | X | 10000 |  |  | 10000 | IGF | Finance Unit

## MID YEAR REVIEW
DEPARTMENT OF AGRICULTURE
2020 ANNUAL ACTION PLAN
S/N | Activity Description | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementation Status | Remarks
|  | IGF | GOG | DONORS | TOTAL COST
1 | Organize two (2) budget sessions, four (4) performance review meetings and submit quarterly and annual reports. |  | 1000 | 15000 | 16000 | DACF, MAG
2 | Pay Office Administrative expenses (Utilities, stationary, equipment repairs, vehicle and motorbike running and maintenance. |  | 1000 | 3000 | 4000 | DACF, MAG
3 | Organize National Farmers’ Day. |  | 65000 |  | 65000 | DACF
4 | Organize extension and research activities. | 9000 | 6000 | 21600 | 36600 | IGF, MAG, DACF
5 | Construct 1No. Abattoir |  | 800000 |  | 800000 | GOG
S/N | Activity Description | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementation Status | Remarks
|  | IGF | GOG | DONORS | TOTAL COST
6 | Organize two (2) capacity building and six (6) trainings sessions for Agric staff. | 3000 | 4000 | 36500 | 43500 | IGF, MAG, DACF
7 | Running of DCACT Secretatriat. |  | 2000 | 6000 | 8000 | DACF, MAG
8 | Procure protective clothings, GPS, programable calculators and office equipment (printer, photocopy. Etc) |  | 21000 | 6500 | 27500 | DACF, MAG
9 | Carry out 1296 home and farm visits and 220 monitoring |  | 16000 | 35000 | 51000 | DACF, MAG
10 | Carry out vaccinations, surveillance and campaign awareness for rabies disease. | 1000 | 2500 | 10700 | 13200 | IGF, MAG, DACF
TRADE AND INDUSTRY
NBSSI 2020 ANNUAL ACTION PLAN
S/N | Activity Description | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementation Status | Remarks
|  | IGF | GOG | DONORS | TOTAL
1 | Trainning in Business innovation/Fishing skills for 30 males |  | 6000 |  | 6000 | DACF
2 | Trainning 30 women in advance soap manufacturing/ marketing |  | 6000 |  | 6000 | DACF
3 | Train 30 people (at least 50% being women) in yoghurt and ice cream production |  | 6000 |  | 6000 | DACF
4 | Support 5 SMEs to attend National Exhibition and Fair ( at least 2 of them should be females) | 5000 |  |  | 5000 | IGF
5 | Organise Trade & Industry Committee Meeting |  | 8000 |  | 8000 | DACF
| Activity Description | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementation Status | Remarks
|  | IGF | GOG | DONORS | TOTAL
6 | 5. Provide business counselling services to SMEs in business registration and payment of DOPs ( 30 males and 40 females) | 8000 |  |  | 8000 | IGF
7 | Organize consultative meeting with banks, Ghana Standard Authority and Registral General Department atleast 50% being females | 5000 |  |  | 5000 | IGF
8 | Train 30 umemployed youth on facial meke up and décor |  | 60000 |  | 6000 | DACF
CO-OPERATIVE
S/N | Activity Description | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementation Status | Remarks
|  | IGF | GOG | DONORS | TOTAL
1 | Organize advance training for 30 women in modern technology in fish processing and marketing |  | 6000 |  | 6000 | DACF
2 | Organize management training for 4 transport Co-operatives’ Executives |  | 5000 |  | 5000 | DACF
3 | Organize technical skills training in the areas of Book-keeping for the staff of the various co-operative groups |  | 10000 |  | 10000 | DACF
S/N | Activity Description | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementation Status | Remarks
|  | IGF | GOG | DONORS | TOTAL
1 | Completion of fence wall around 2No. CHPs Compound |  | 250000 |  | 250000 | DACF
2 | Completion of a 20 bed capacity isolation ward at the Ashaiman polyclinic |  | 40000 |  | 40000 | DACF
3 | Purchase 1No. anesthetic machine for Ashaiman Polyclinic |  |  | 150000 | 150000 | Rotary Club, Ghana
4 | Procure furniture and equipment for new male and female wards at the polyclinic and Tsui Bleoo CHPs Compund |  | 90000 |  | 90000 | DACF
5 | Support for lmmunisation Programmes |  | 40000 |  | 40000 | DACF
6 | Caryout disease surveillance and control and containment activities |  | 10000 |  | 10000 | DACF
S/N | Activity Description | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementation Status | Remarks
|  | IGF | GOG | DONORS | TOTAL
7 | Organise Public Health Emergency Committee | 10000 |  |  | 10000 | IGF
8 | Organise quarterly Municipal Health Oversight Committee Meetings | 10000 |  |  | 10000 | IGF
9 | Undertake mid-year performance review meeting |  | 33500 |  | 33500 | DACF
10 | Suppot Health Directors' Annual Conference |  | 7000 |  | 7000 | DACF
11 | Undertake roll back maleria programme (monitoring , screening and treatment, operational research, data validation and management) |  | 77688.37 |  | 77688.37 | DACF
S/N | Activity Description | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementation Status | Remarks
|  | IGF | GOG | DONORS | TOTAL
12 | Undertake HIV/AIDS programme (support) screening, monitoring, training, data validation etc.) in the municipality |  |  | 77688.37 | 77688.37 | MSHARP
S/N | Activity Description | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementation Status | Remarks
|  | IGF | GOG | DONORS | TOTAL
1 | Organize My First Day at School for P1 and KGs in the Municipality |  | 25000 |  | 25000 | DACF
2 | Organize STMIE Clinics |  | 17500 |  | 17500 | DACF
3 | Organize and participate in Municipal and Regional Cultural Festival of Arts |  | 15000 |  | 15000 | DACF
4 | Support for BECE |  | 40000 |  | 40000 | DACF
5 | Support for best teacher awards |  | 20000 |  | 20000 | DACF
6 | Organise Municipal Education Oversight Committee meeting | 6000 |  |  | 6000 | IGF
7 | Education fund |  | 155376.75 |  | 155376.75 | DACF
S/N | Activity Description | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementation Status | Remarks
|  | IGF | GOG | DONORS | TOTAL COST
8 | Organise Municipal SPAM | 5000 |  |  | 5000 | IGF
S/N | Activity Description | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementation Status | Remarks
|  | IGF | GOG | DONORS | TOTAL
1 | Awareness creation on Functional literacy/ JHS and SHS remedial classes |  | 5000 |  | 5000 | DACF
2 | Establishment of 30 English classes 2 local language classes | 2000 |  |  | 2000 | IGF
3 | Undertake Quarterly Monitoring and Evaluation of Non-formal Education |  | 3000 |  | 3000 | DACF
S/N | Activity Description | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementation Status | Remarks
|  | IGF | GOG | DONORS | TOTAL
1 | Establish data base for all sports clubs in the Municipality | 2000 |  |  | 2000 | IGF
2 | Organise Municipal sports tournaments for selected teams | 8000 |  |  | 8000 | IGF
3 | Undertake regional sports festival |  | 5000 |  | 5000 | DACF
S/N | Activity Description | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementation Status | Remarks
|  | IGF | GOG | DONORS | TOTAL
1 | Undertake child non maintainace cases, family reconcilation/counselling |  | 4000 |  | 4000 | DACF
2 | Monitor the utilization of 3% of the DACF given to PWDs and other programmes |  | 4500 |  | 4500 | Disability Common Fund
3 | Monitor LEAP payment bi-monthly |  | 5000 |  | 5000 | DACF
4 | Undertake Juvenile Justice Administration |  | 6000 |  | 6000 | DACF
5 | Reintegration of missing/abandoned Children with families |  | 7000 |  | 7000 | DACF
6 | Celebrate World Day Against Child Labour |  | 3408 |  | 3408 | DACF
S/N | Activity Description | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementation Status | Remarks
|  | IGF | GOG | DONORS | TOTAL COST
7 | Inspection of early childhood centers/registration |  | 4000 |  | 4000 | DACF
8 | Organise eight (8) mass meetings, Home Visits and Demonstrations for 850 participants. (800 women and 50 men). |  |  | 10000 | 10000 | Donors
9 | Organise two (2) Workshops on Skills Training and Extension Services for 600 participants. (550 women and 50 men). | 3500 | 3500 | 3000 | 10000 | DACF, IGF & Donors
10 | Organise income generating activities such as Soap and Bead making for 600 participants (550 women and 50 men). |  | 10000 |  | 10000 | DACF
S/N | Activity Description | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementation Status | Remarks
|  | IGF | GOG | DONORS | TOTAL COST
1 | Desilt drainsand sweeping streets in the Municipality |  | 100000 |  | 100000 | DACF
2 | Procure cleaning materials for Assembly |  | 20000 |  | 20000 | DACF
3 | Organize 12 monthly clean-up exercise | 106000 | 84000 |  | 190000 | IGF, DACF
4 | Conduct medical screening of 4500 food vendors | 5000 |  |  | 5000 | IGF
5 | Prosecute sanitary offenders | 6000 |  |  | 6000 | IGF
6 | Organise 3 public education on environmental health promotion | 10000 |  | - |  | -
7 | Bury unclaimed paupers | 5000 |  |  | 5000 | IGF
8 | Procure working tools and materials for sanitation management |  | 25000 |  | 25000 | DACF
S/N | Activity Description | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementation Status | Remarks
|  | IGF | GOG | DONORS | TOTAL COST
9 | Facilitate the construction of 300 household toilet |  |  |  |  | GAMA
10 | Conduct fumigation exercises | 10000 | 20000 |  | 30000 | IGF DACF
11 | Organise 4No. evacuation of solid wate at unauthorised areas | 15000 | 20000 |  | 35000 | IGF DACF
S/N | Activity Description | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementation Status | Remarks
|  | IGF | GOG | DONORS | TOTAL COST
76 | Grading and gravelling of selected roads |  | 400000 |  | 400000 | DACF
77 | Construction of drains on selected roads |  |  | 4000000 | 4000000 | GAMA
78 | Rehabilitate Kofi Nimo Street / Tema International Sch. Roads |  | 2500000 |  | 2500000 | GOG
79 | Rehabilitate School Road, Channel 11 Road, Ecuado Road Danquah Road (3.2km) |  | 6862179.44 |  | 6862179.44 | GOG
80 | Desilting of drains | 100000 | 100000 |  | 200000 | IGF, DACF
81 | Construct 5no. Pipe culvert at selected locations | 150000 |  |  | 150000 | IGF
S/N | Activity Description | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementation Status | Remarks
|  | IGF | GOG | DONORS | TOTAL COST
82 | Construct selected drains within Lebanon Zone-1 to Zone 5 |  | 666524.54 |  | 666524.54 | DPAT Fund
83 | Traffic Management and Safety | 100000 |  |  | 100000 | IGF
NAME OF DEPARTMENT: Physical Planning
PLAN
S/N | Activity Description | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementation Status | Remarks
|  | IGF | GOG | DONORS | TOTAL COST
1 | Secure documents on Assembly lands |  | 50000 |  | 50000 | DACF
2 | Organise 4No. SAT meetings |  | 12000 |  | 12000 | DACF
3 | Organise 6No. Spatial Planning Committee, 12No. Technical Committee meetings |  | 48000 |  | 48000 | DACF
4 | Organise sensitisation workshop on permiting process |  | 10000 |  | 10000 | DACF
5 | Preparation of structure plan and local plans for selected communities |  | 45000 |  | 45000 | DACF
Programme Area: Environment Infrastructure and Human Settlements
Sub- Programme: Disaster Prevention and Management
S/N | Activity Description | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementation Status | Remarks
|  | IGF | GOG | DONORS | TOTAL COST
89 | Undertake Vulnerability and risk assessments |  | 7860 |  | 7860 | DACF
90 | Organise quarterly public education on disaster prevention and management |  | 16000 |  | 16000 | DACF
91 | Identify and Map out Hazard areas | 4000 |  |  | 4000 | IGF
92 | Organise mid-year and annual performance review neetings with stakeholders: DMC(15), HOD(6), ZC/ZS(14) |  | 5000 |  | 5000 | DACF
93 | Greening City |  | 25000 |  | 25000 | DACF
94 | Dredging of Gbemi river basins |  | 100000 |  | 100000 | DACF
Programme Area: Environment Infrastructure and Human Settlements
Sub- Programme: Disaster Prevention and Management
S/N | Activity Description | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementation Status | Remarks
|  | IGF | GOG | DONORS
95 | Train Disaster Volunteer Clubs in Schools (50) and Disaster Volunteer Groups(50) |  | 4000 |  | 4000 | DACF
96 | Organise International Day for Disaster Risk Reduction (IDDR) Celebration(13th October) | 8000 |  |  | 8000 | IGF
S/N | Activity Description | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementation Status | Remarks
|  | IGF | GOG | DONORS | TOTAL COST
1 | Create Community level awareness on the importance of citizens active involvement in local governance and peaceful election | 20000 |  |  | 20000 | IGF
2 | Sensitize communities in 17 electoral areas on their Civil rights |  | 5000 |  | 5000 | DACF
3 | Organise Sensitization Program for 150 women on domestic voilence against women and early child marriage |  | 10000 |  | 10000 | DACF
S/N | Activity Description | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementation Status | Remarks
|  | IGF | GOG | DONORS | TOTAL
1 | Pay Stafff welfare and medical expenses | 63000 |  |  | 63000 | IGF
2 | Organise seminars/ conference/ worshops/ meetings | 233500 |  |  | 233500 | IGF
3 | Pay Library and subscription, postal charges | 15000 |  |  | 15000 | IGF
4 | Pay Donations | 80000 |  |  | 80000 | IGF
5 | Best worker awards and rewards | 50000 |  |  | 50000 | IGF
6 | Pay salaries of casual labourers | 929291.01 |  |  | 929291.01 | IGF
7 | Pay hotel Accommodation | 50000 |  |  | 50000 | IGF
8 | Pay allawances for offical Assignment (Honorarium, out of station allowance, T&T) | 597000 |  |  | 597000 | IGF
9 | Support Traditional Council | 20000 |  |  | 20000 | IGF
10 | Maitenance of official vehicle | 450000 |  |  | 450000 | IGF
11 | Procure fuel and lubricants for official vehicles | 300000 |  |  | 300000 | IGF
12 | Rental of vehicles | 20000 |  |  | 20000 | IGF
13 | Printed Materials and Stationery | 400000 |  |  | 400000 | IGF
14 | Foreign Travel cost and expenses | 50000 |  |  | 50000 | IGF
15 | Local Travel cost and expenses | 50000 |  |  | 50000 | IGF
16 | Maintenace of furniture and Fixtures | 30000 |  |  | 30000 | IGF
17 | Maintenace of General Equipment/ plant | 23000 |  |  | 23000 | IGF
18 | Procure office facilities, supplies and accessories |  | 200000 |  | 200000 | DACF
19 | Pay utility Charges | 214000 |  |  | 214000 | IGF
20 | Undertake Operational enhancement expenses | 120000 |  |  | 120000 | IGF
21 | Official celebrations/ceremonial functions, state protocol service/ end of year | 80000 |  |  | 80000 | IGF
22 | Payment of Transfer Grants |  | 100000 |  | 100000 | DACF
23 | Pay bank Charges |  | 75000 |  | 75000 | DACF
24 | Organise education on Payment of Taxes and Rates for 60 youth groups, churches and Mosques | 8000 |  |  | 8000 | IGF
25 | Prepare and gazette 2021 FFR |  | 70000 |  | 70000 | DACF
26 | Prepare 2021 composite AAP and Budget |  | 120000 |  | 120000 | DACF
27 | Sponsor 3 middle mgt staff to attend ILGS Maters Degree programme |  |  |  | 30000 | DACF
28 | Sponsor 3 staff for continuous professional development (Finance & Audit, MCD) |  | 20000 |  | 20000 | DACF
29 | Prepare and submit internal audit report | 20000 |  |  | 20000 | IGF
30 | Serminars/conferences/workshops/meetings expenses-management, budget committee, MPCU, MEOC, entity tender committees, Audit committee, NHOC and other technical committee meetings | 60000 |  |  | 60000 | IGF
31 | Pay External consultants | 30000 |  |  | 30000 | IGF
32 | Counterpart fund (Construction of Artisana Village) |  | 150000 |  | 150000 | DACF
33 | Serminars/conferences/media/workshops (local)- AAP, Plan reviews, Monitoring and Evaluation including elections, Budget reviews, Budget dissermination, Budget hearings and Social Accountability forum |  | 150000 |  | 150000 | DACF
34 | Conduct routine maintenance of sewer lines | 10000 |  |  | 10000 | IGF
35 | Educate rate payers on the need to pay rates promptly | 80000 |  |  | 80000 | IGF
36 | GAMA operational expenses |  |  | 100000 | 100000
37 | Board/Committees/Commission Allawance/ General Assembly | 590000 |  |  | 590000 | IGF
38 | Support to lower Structure |  | 155376.75 |  | 155376.75 | DACF
39 | Pay Assembly members mobilization | 210000 |  |  | 210000 | IGF
40 | Pay for community engagement by Assembly members | 142800 |  |  | 142800 | IGF
41 | Support to community innited projects |  | 338441.74 |  | 338441.74 | DACF
42 | Support to security services |  | 150000 |  | 150000 | DACF
43 | Monitoring and evaluation of Assembly programmes and projects |  | 120000 |  | 120000 | DACF
44 | Train women in lobbying and advocacy skills | 2000 |  | 10000 | 12000 | GIZ, IGF
45 | Election support | 250000 | 250000 |  | 500000 | IGF, DACF
S/N | Activity Description | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementation Status | Remarks
|  | IGF | GOG | DONORS | TOTAL
1 | Organise 2 No. capacity programmes for transport operators and other stakeholders in Ashaiman | 3000 |  |  | 3000 | IGF
2 | Organise two (2) stakeholder meetings to facilitate institutional collaboration between the enforcement unit of the Assembly and other enforcement agencies | 5000 |  |  | 5000 | IGF
3 | Train 2 UPTU staffs in Transport planning | 5000 |  |  | 5000 | IGF
4 | Update Passenger Transport Database | 4000 |  |  | 4000 | IGF
5 | Regulate activities of vehicle terminals | 1000 |  |  | 1000 | IGF
Programme Area: Governace, Corruption and Adminstration
Sub-Programme: Finance and Revenue Administration
S/N | Activity Description | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementation Status | Remarks
|  | IGF | GOG | DONORS | TOTAL
Programme Area: Governace, Corruption and Adminstration
FINANCE (2020 ANNUAL ACTION PLAN)
S/N | Activity Description | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementation Status | Remarks
|  | IGF | GOG | DONORS | TOTAL
1 | Undertake Property Evaluation and Validation | 150000 |  |  | 150000
2 | Organize Revenue performance review | 8600 |  |  | 8600 | IGF
3 | Prepare monthly and annual accounts | 10000 |  |  | 10000 | IGF
4 | Purchase value books | 100000 |  |  | 100000 | IGF
5 | Pay allawaces for Revenue Mobilisation mob-up | 84000 |  |  | 84000 | IGF
6 | Construct 2No.pay point at market sequence | 40000 |  |  | 40000 | IGF
7 | Undertake Monitoring and supervision of Revenue mobilization activities | 20000 |  |  | 20000 | IGF
NAME OF DEPARTMENT: WORKS
2020 ANNUAL ACTION PLAN
S/N | Activity Description | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementation Status | Remarks
|  | IGF | GOG | DONORS | TOTAL
1 | Outstanding paymenty of fence wall around ASHMA No.4 Basic School |  | 380000 |  | 200000 | DACF
2 | Rehablitate 2no. Basic Schools Block |  | 250000 |  | 250000 | DACF
3 | Supply 100 specialised table with 500 chairs for KGs and 300 dual desk for basic sch. |  | 170000 |  | 170000 | DACF
4 | Construct and mechanise 5No. Instituitional Boreholes |  | 125000 |  | 125000 | DACF
5 | Completion of fence wall and land scapping of MCE residence (work-in-progress) | 100000 | 350000 |  | 450000 | IGF, DACF
6 | Furnishing of MCE official residence |  | 250000 |  | 250000 | DACF
7 | Complete the construction of 2-storey office complex for ASHMA |  | 20000 |  | 20000 | DACF
8 | Rehabilitate and install new streetlights | 120000 | 345000 |  | 465000 | DACF, IGF
9 | Construct a sewer system |  |  |  |  | GAMA
10 | Outstanding payment of 2No. Fence wall around CHPs Compand |  | 380605
11 | payment of outstanding project- Tulaku CHPs Compund |  | 97000
12 | Construction of 2No. 20-steater Instituitional Toilet |  |  | 2010560
13 | Rehabilitation of Butchers shop |  | 165940
S/N | Activity Description | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementation Status | Remarks
|  | IGF | GOG | DONORS | TOTAL
1 | Provide 2-day training on LGS Protocols |  | 12000 |  | 12000 | DACF
2 | Train Revenue collectors/ Data billing personnel | 49000 |  |  | 49000 | IGF
3 | Train Assembly members on budget and plan preparation, Local Governance System |  | 20000 |  | 20000 | DACF
4 | Organise orientation for 2020-2021 national service personel | 5000 |  |  | 5000 | IGF
5 | Organise training programme for the taskforce of the Assembly |  | 10000 |  | 10000 | DACF
S/N | Activity Description | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementation Status | Remarks
|  | IGF | GOG | DONORS | TOTAL
1 | Organise 4 Town Hall meetings |  | 98000 |  | 98000 | DACF
2 | Quarterly MCE's visit to electoral areas |  | 51000 |  | 51000 | DACF
3 | Organise public education on the functions of the Assembly | 24000 |  |  | 24000 | IGF

## Mid Year Review2
DEPARTMENT OF AGRICULTURE
REVIEW APPROVED 2020 ANNUAL ACTION PLAN
S/N | Activity Description | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementation Status | Remarks
|  | IGF | GOG | DONORS | TOTAL COST
1 | Organize two (2) budget sessions, four (4) performance review meetings and submit quarterly and annual reports. |  | 1000 | 15000 | 16000 | DACF, MAG
2 | Pay Office Administrative expenses (Utilities, stationary, equipment repairs, vehicle and motorbike running and maintenance. |  | 1000 | 3000 | 4000 | DACF, MAG
3 | Organize National Farmers’ Day. |  | 65000 |  | 65000 | DACF
4 | Organize extension and research activities. | 9000 | 6000 | 21600 | 36600 | IGF, MAG, DACF
6 | Organize two (2) capacity building and six (6) trainings sessions for Agric staff. | 3000 | 4000 | 36500 | 43500 | IGF, MAG, DACF
7 | Running of DCACT Secretatriat. |  | 2000 | 6000 | 8000 | DACF, MAG
8 | Procure protective clothings, GPS, programable calculators and office equipment (printer, photocopy. Etc) |  | 21000 | 6500 | 27500 | DACF, MAG |  | DELETE
9 | Carry out 1296 home and farm visits and 220 monitoring |  | 16000 | 35000 | 51000 | DACF, MAG |  | REDUCE M&E TO 150
10 | Carry out vaccinations, surveillance and campaign awareness for rabies disease. | 1000 | 2500 | 10700 | 13200 | IGF, MAG, DACF
11 | Rehabilitation of Butchers shop |  | 165940 |  | 165940
12 | Construct 1No. Abattoir |  | 800000 |  | 800000 | GOG |  | DELETE
1230740
TRADE AND INDUSTRY
NBSSI 2020 APPROVED ANNUAL ACTION PLAN
S/N | Activity Description | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementation Status | Remarks
|  | IGF | GOG | DONORS | TOTAL
1 | Trainning in Business innovation/Fishing skills for 30 males |  | 6000 |  | 6000 | DACF
2 | Trainning 30 women in advance soap manufacturing/ marketing |  | 6000 |  | 6000 | DACF
3 | Train 30 people (at least 50% being women) in yoghurt and ice cream production |  | 6000 |  | 6000 | DACF
4 | Support 5 SMEs to attend National Exhibition and Fair ( at least 2 of them should be females) | 5000 |  |  | 5000 | IGF
5 | Organise Trade & Industry Committee Meeting |  | 8000 |  | 8000 | DACF
6 | 5. Provide business counselling services to SMEs in business registration and payment of DOPs ( 30 males and 40 females) | 8000 |  |  | 8000 | IGF
7 | Organize consultative meeting with banks, Ghana Standard Authority and Registral General Department atleast 50% being females | 5000 |  |  | 5000 | IGF
8 | Train 30 umemployed youth on facial meke up and décor |  | 60000 |  | 6000 | DACF
50000
TRADE AND INDUSTRY
CO-OPERATIVE 2020 APPROVED ANNUAL ACTION PLAN
S/N | Activity Description | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementation Status | Remarks
|  | IGF | GOG | DONORS | TOTAL
1 | Organize advance training for 30 women in modern technology in fish processing and marketing |  | 6000 |  | 6000 | DACF
2 | Organize management training for 4 transport Co-operatives’ Executives |  | 5000 |  | 5000 | DACF
3 | Organize technical skills training in the areas of Book-keeping for the staff of the various co-operative groups |  | 10000 |  | 10000 | DACF
21000
MUNICIPAL HEALTH DIRECTORATE
S/N | Activity Description | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementation Status | Remarks
|  | IGF | GOG | DONORS | TOTAL
1 | Purchase 1No. anesthetic machine for Ashaiman Polyclinic |  |  | 150000 | 150000 | Rotary Club, Ghana |  | roll over and change the funding source
2 | Procure furniture and equipment for new male and female wards at the polyclinic and Tsui Bleoo CHPs Compund |  | 90000 |  | 90000 | DACF |  | delete amle and female ward and maintain the chps compund
3 | Support for lmmunisation Programmes |  | 40000 |  | 40000 | DACF
4 | Caryout disease surveillance and control and containment activities |  | 10000 |  | 10000 | DACF
5 | Organise Public Health Emergency Committee | 10000 |  |  | 10000 | IGF
6 | Organise quarterly Municipal Health Oversight Committee Meetings | 10000 |  |  | 10000 | IGF
7 | Undertake mid-year performance review meeting |  | 33500 |  | 33500 | DACF
8 | Suppot Health Directors' Annual Conference |  | 7000 |  | 7000 | DACF
9 | Undertake roll back maleria programme (monitoring , screening and treatment, operational research, data validation and management) |  | 77688.37 |  | 77688.37 | DACF
10 | Undertake HIV/AIDS programme (support) screening, monitoring, training, data validation etc.) in the municipality |  |  | 77688.37 | 77688.37 | MSHARP
11 | Outstanding payment of 2No. Fence wall around CHPs Compand |  | 380605 |  | 380605
12 | payment of outstanding project- Tulaku CHPs Compund |  | 97000 |  | 97000 |  |  | part payment made
983481.74
MUNICIPAL EDUCATION DIRECTORATE
S/N | Activity Description | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementation Status | Remarks
|  | IGF | GOG | DONORS | TOTAL
1 | Organize STMIE Clinics |  | 17500 |  | 17500 | DACF
2 | Organize and participate in Municipal and Regional Cultural Festival of Arts |  | 15000 |  | 15000 | DACF
3 | Support for BECE |  | 40000 |  | 40000 | DACF
4 | Support for best teacher awards |  | 20000 |  | 20000 | DACF
5 | Organise Municipal Education Oversight Committee meeting | 6000 |  |  | 6000 | IGF
6 | Organise Municipal SPAM | 5000 |  |  | 5000 | IGF
7 | Organize My First Day at School for P1 and KGs in the Municipality |  | 25000 |  | 25000 | DACF
8 | Education fund |  | 155376.75 |  | 155376.75 | DACF
9 | Outstanding paymenty of fence wall around ASHMA No.4 Basic School |  | 380000 |  | 200000 | DACF
10 | Rehablitate 2no. Basic Schools Block |  | 250000 |  | 250000 | DACF
11 | Supply 100 specialised table with 500 chairs for KGs and 300 dual desk for basic sch. |  | 170000 |  | 170000 | DACF
| TOTAL |  |  |  | 903876.75
NON FORMAL EDUCATION
APPROVED 2020 ANNUAL ACTION PLAN
S/N | Activity Description | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementation Status | Remarks
|  | IGF | GOG | DONORS | TOTAL
1 | Awareness creation on Functional literacy/ JHS and SHS remedial classes |  | 5000 |  | 5000 | DACF
2 | Establishment of 30 English classes 2 local language classes | 2000 |  |  | 2000 | IGF
3 | Undertake Quarterly Monitoring and Evaluation of Non-formal Education |  | 3000 |  | 3000 | DACF |  | carry out 3 m&e
| TOTAL |  |  |  | 10000
SPORTS
APPROVED 2020 ANNUAL ACTION PLAN
S/N | Activity Description | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementation Status | Remarks
|  | IGF | GOG | DONORS | TOTAL
1 | Establish data base for all sports clubs in the Municipality | 2000 |  |  | 2000 | IGF
2 | Organise Municipal sports tournaments for selected teams | 8000 |  |  | 8000 | IGF
3 | Undertake regional sports festival |  | 5000 |  | 5000 | DACF
| TOTAL |  |  |  | 15000
SOCIAL WELFARE AND COMMUNITY DEVELOPMENT
APPROVED 2020 ANNUAL ACTION PLAN
S/N | Activity Description | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementation Status | Remarks
|  | IGF | GOG | DONORS | TOTAL
1 | Undertake child non maintainace cases, family reconcilation/counselling |  | 4000 |  | 4000 | DACF
2 | Monitor the utilization of 3% of the DACF given to PWDs and other programmes |  | 4500 |  | 4500 | Disability Common Fund
3 | Monitor LEAP payment bi-monthly |  | 5000 |  | 5000 | DACF
4 | Undertake Juvenile Justice Administration |  | 6000 |  | 6000 | DACF
5 | Reintegration of missing/abandoned Children with families |  | 7000 |  | 7000 | DACF
6 | Celebrate World Day Against Child Labour |  | 3408 |  | 3408 | DACF
7 | Inspection of early childhood centers/registration |  | 4000 |  | 4000 | DACF |  | reduction in amount
| TOTAL |  |  |  | 33908
COMMUNITY DEVELOPMENT
S/N | Activity Description | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementation Status | Remarks
|  | IGF | GOG | DONORS | TOTAL COST
8 | Organise eight (8) mass meetings, Home Visits and Demonstrations for 850 participants. (800 women and 50 men). |  |  | 10000 | 10000 | Donors
9 | Organise two (2) Workshops on Skills Training and Extension Services for 600 participants. (550 women and 50 men). | 3500 | 3500 | 3000 | 10000 | DACF, IGF & Donors
10 | Organise income generating activities such as Soap and Bead making for 600 participants (550 women and 50 men). |  | 10000 |  | 10000 | DACF
| TOTAL |  |  |  | 30000
ENVIRONMENTAL HEALTH UNIT
APPROVED 2020 ANNUAL ACTION PLAN
S/N | Activity Description | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementation Status | Remarks
|  | IGF | GOG | DONORS | TOTAL COST
1 | Desilt drains and sweeping streets in the Municipality |  | 100000 |  | 100000 | DACF
2 | Procure cleaning materials for Assembly |  | 20000 |  | 20000 | DACF
3 | Organize 12 monthly clean-up exercise | 106000 | 84000 |  | 190000 | IGF, DACF
4 | Conduct medical screening of 4500 food vendors | 5000 |  |  | 5000 | IGF
5 | Prosecute sanitary offenders | 6000 |  |  | 6000 | IGF
6 | Organise 3 public education on environmental health promotion | 10000 |  | - | 10000 | -
7 | Bury unclaimed paupers | 5000 |  |  | 5000 | IGF
8 | Procure working tools and materials for sanitation management |  | 25000 |  | 25000 | DACF
9 | Conduct fumigation exercises | 10000 | 20000 |  | 30000 | IGF DACF
10 | Organise 4No. evacuation of solid wate at unauthorised areas | 15000 | 20000 |  | 35000 | IGF DACF |  | reduce to 2No.
11 | Construct and mechanise 5No. Instituitional Boreholes |  | 125000 |  | 125000 | DACF/ DPAT |  | isolate and reduce to 2no.
12 | Construct a sewer system |  |  |  |  | GAMA
13 | Construction of 2No. 20-steater Instituitional Toilet |  |  | 2010560 | 2010560
| TOTAL |  |  |  | 2561560
14 | Facilitate the construction of 300 household toilet |  |  |  |  | GAMA
DEPARTMENT OF URBAN ROADS
APPROVED 2020 ANNUAL ACTION PLAN
S/N | Activity Description | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementation Status | Remarks
|  | IGF | GOG | DONORS | TOTAL COST
1 | Grading and gravelling of selected roads |  | 400000 |  | 0 | DACF/ ROAD FUND
2 | Construction of drains on selected roads |  |  | 4000000 | 4000000 | GAMA |  | 800000
3 | Rehabilitate Kofi Nimo Street / Tema International Sch. Roads |  | 2500000 |  | 2500000 | GOG
4 | Rehabilitate School Road, Channel 11 Road, Ecuado Road Danquah Road (3.2km) |  | 6862179.44 |  | 6862179.44 | GOG
5 | Desilting of drains | 100000 | 100000 |  | 200000 | IGF, DACF |  | ROAD FUND
6 | Construct 5no. Pipe culvert at selected locations | 150000 |  |  | 150000 | IGF |  | Minor drainage repairs (grf)
7 | Construct selected drains within Lebanon Zone-1 to Zone 5 |  | 666524.54 |  | 666524.54 | DPAT Fund
8 | Traffic Management and Safety | 100000 |  |  | 100000 | GRF
| TOTAL |  |  |  | 14478703.98
PHYSICAL PLANNING
APPROVED 2020 ANNUAL ACTION PLAN
S/N | Activity Description | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementation Status | Remarks
|  | IGF | GOG | DONORS | TOTAL COST
1 | Secure documents on Assembly lands |  | 50000 |  | 50000 | DACF |  | ROLL OVER
2 | Organise 4No. SAT meetings |  | 12000 |  | 12000 | DACF
3 | Organise 6No. Spatial Planning Committee, 12No. Technical Committee meetings |  | 48000 |  | 48000 | DACF |  | Organise 2No. Spatial Planning Committee, 2No. Technical Committee meetings
4 | Organise sensitisation workshop on permiting process |  | 10000 |  | 10000 | DACF |  | ROLL OVER
5 | Preparation of structure plan and local plans for selected communities |  | 45000 |  | 45000 | DACF |  | DELETE
| TOTAL |  |  |  | 165000
NADMO
APPROVED 2020 ANNUAL ACTION PLAN
S/N | Activity Description | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementation Status | Remarks
|  | IGF | GOG | DONORS | TOTAL COST
1 | Undertake Vulnerability and risk assessments |  | 7860 |  | 7860 | DACF
2 | Organise quarterly public education on disaster prevention and management |  | 16000 |  | 16000 | DACF
3 | Identify and Map out Hazard areas | 4000 |  |  | 4000 | IGF
4 | Organise mid-year and annual performance review neetings with stakeholders: DMC(15), HOD(6), ZC/ZS(14) |  | 5000 |  | 5000 | DACF
5 | Greening City |  | 25000 |  | 25000 | DACF
6 | Dredging of Gbemi river basins |  | 100000 |  | 100000 | DACF
7 | Train Disaster Volunteer Clubs in Schools (50) and Disaster Volunteer Groups(50) |  | 4000 |  | 4000 | DACF
8 | Organise International Day for Disaster Risk Reduction (IDDR) Celebration(13th October) | 8000 |  |  | 8000 | IGF
| TOTAL |  |  |  | 169860
governance
S/N | Activity Description | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementation Status | Remarks
|  | IGF | GOG | DONORS | TOTAL COST
1 | Create Community level awareness on the importance of citizens active involvement in local governance and peaceful election | 20000 |  |  | 20000 | IGF
2 | Sensitize communities in 17 electoral areas on their Civil rights |  | 5000 |  | 5000 | DACF
3 | Organise Sensitization Program for 150 women on domestic voilence against women and early child marriage |  | 10000 |  | 10000 | DACF
4 | Pay Stafff welfare and medical expenses | 63000 |  |  | 63000 | IGF
5 | Organise seminars/ conference/ worshops/ meetings | 233500 |  |  | 233500 | IGF
6 | Pay Library and subscription, postal charges | 15000 |  |  | 15000 | IGF
7 | Pay Donations | 80000 |  |  | 80000 | IGF
8 | Best worker awards and rewards | 50000 |  |  | 50000 | IGF |  | DELETE
9 | Pay salaries of casual labourers | 929291.01 |  |  | 929291.01 | IGF
10 | Pay hotel Accommodation | 50000 |  |  | 50000 | IGF
11 | Pay allawances for offical Assignment (Honorarium, out of station allowance, T&T) | 597000 |  |  | 597000 | IGF
12 | Support Traditional Council | 20000 |  |  | 20000 | IGF
13 | Maintenance of official vehicle | 450000 |  |  | 450000 | IGF
14 | Procure fuel and lubricants for official vehicles | 300000 |  |  | 300000 | IGF
15 | Rental of vehicles | 20000 |  |  | 20000 | IGF
16 | Printed Materials and Stationery | 400000 |  |  | 400000 | IGF
17 | Foreign Travel cost and expenses | 50000 |  |  | 50000 | IGF |  | DELETE
18 | Local Travel cost and expenses | 50000 |  |  | 50000 | IGF
19 | Maintenace of furniture and Fixtures | 30000 |  |  | 30000 | IGF
20 | Maintenace of General Equipment/ plant | 23000 |  |  | 23000 | IGF
21 | Procure office facilities, supplies and accessories |  | 200000 |  | 200000 | DACF
22 | Pay utility Charges | 214000 |  |  | 214000 | IGF
23 | Undertake Operational enhancement expenses | 120000 |  |  | 120000 | IGF
24 | Official celebrations/ceremonial functions, state protocol service/ end of year | 80000 |  |  | 80000 | IGF
25 | Payment of Transfer Grants |  | 100000 |  | 100000 | DACF
26 | Pay bank Charges |  | 75000 |  | 75000 | DACF
27 | Organise education on Payment of Taxes and Rates for 60 youth groups, churches and Mosques | 8000 |  |  | 8000 | IGF
28 | Prepare and gazette 2021 FFR |  | 70000 |  | 70000 | DACF
29 | Prepare 2021 composite AAP and Budget |  | 120000 |  | 120000 | DACF
30 | Sponsor 3 middle mgt staff to attend ILGS Maters Degree programme |  |  |  | 30000 | DACF |  | DELETE
31 | Sponsor 3 staff for continuous professional development (Finance & Audit, MCD) |  | 20000 |  | 20000 | DACF
32 | Prepare and submit internal audit report | 20000 |  |  | 20000 | IGF
33 | Serminars/conferences/workshops/meetings expenses-management, budget committee, MPCU, MEOC, entity tender committees, Audit committee, NHOC and other technical committee meetings | 60000 |  |  | 60000 | IGF
34 | Pay External consultants | 30000 |  |  | 30000 | IGF
35 | Counterpart fund (Construction of Artisana Village) |  | 150000 |  | 150000 | DACF
36 | Serminars/conferences/media/workshops (local)- AAP, Plan reviews, Monitoring and Evaluation including elections, Budget reviews, Budget dissermination, Budget hearings and Social Accountability forum |  | 150000 |  | 150000 | DACF
37 | Conduct routine maintenance of sewer lines | 10000 |  |  | 10000 | IGF |  | DELETE
38 | Educate rate payers on the need to pay rates promptly | 80000 |  |  | 80000 | IGF
39 | GAMA operational expenses |  |  | 100000 | 100000
40 | Board/Committees/Commission Allawance/ General Assembly | 590000 |  |  | 590000 | IGF
41 | Support to sub Structure |  | 155376.75 |  | 155376.75 | DACF
42 | Pay Assembly members mobilization | 210000 |  |  | 210000 | IGF
43 | Pay for community engagement by Assembly members | 142800 |  |  | 142800 | IGF
44 | Support to community innited projects |  | 338441.74 |  | 338441.74 | DACF
45 | Support to security services |  | 150000 |  | 150000 | DACF
46 | Monitoring and evaluation of Assembly programmes and projects |  | 120000 |  | 120000 | DACF
47 | Train women in lobbying and advocacy skills | 2000 |  | 10000 | 12000 | GIZ, IGF |  | delete
48 | Election support | 250000 | 250000 |  | 500000 | IGF, DACF
49 | Quarterly MCE's visit to electoral areas |  | 51000 |  | 51000 | DACF
50 | Completion of fence wall and land scapping of MCE residence (work-in-progress) | 100000 | 350000 |  | 450000 | IGF, DACF
51 | Furnishing of MCE official residence |  | 250000 |  | 250000 | DACF
52 | Complete the construction of 2-storey office complex for ASHMA |  | 20000 |  | 20000 | DACF
53 | Rehabilitate and install new streetlights | 120000 | 345000 |  | 465000 | DACF, IGF
8487409.5
DEPARTMENT OF URBAN TRANSPORT
APPROVED 2020 ANNUAL ACTION PLAN
S/N | Activity Description | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementation Status | Remarks
|  | IGF | GOG | DONORS | TOTAL
1 | Organise 2 No. capacity programmes for transport operators and other stakeholders in Ashaiman | 3000 |  |  | 3000 | IGF
2 | Organise two (2) stakeholder meetings to facilitate institutional collaboration between the enforcement unit of the Assembly and other enforcement agencies | 5000 |  |  | 5000 | IGF
3 | Train 2 UPTU staffs in Transport planning | 5000 |  |  | 5000 | IGF
4 | Update Passenger Transport Database | 4000 |  |  | 4000 | IGF
5 | Regulate activities of vehicle terminals | 1000 |  |  | 1000 | IGF
| TOTAL |  |  |  | 18000
FINANCE (2020 ANNUAL ACTION PLAN)
S/N | Activity Description | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementation Status | Remarks
|  | IGF | GOG | DONORS | TOTAL
1 | Undertake Property Evaluation and Validation | 150000 |  |  | 150000 |  |  | LISTING OF BUSINESS PROPERTIES ROLL OVER AND REDUCE
2 | Organize Revenue performance review | 8600 |  |  | 8600 | IGF
3 | Prepare monthly and annual accounts | 10000 |  |  | 10000 | IGF
4 | Purchase value books | 100000 |  |  | 100000 | IGF
5 | Pay allawaces for Revenue Mobilisation mob-up | 84000 |  |  | 84000 | IGF
6 | Construct 2No.pay point at market sequence | 40000 |  |  | 40000 | IGF |  | 3no. PAYPOINTS
7 | Undertake Monitoring and supervision of Revenue mobilization activities | 20000 |  |  | 20000 | IGF
| TOTAL |  |  |  | 412600
NAME OF DEPARTMENT: WORKS
2020 ANNUAL ACTION PLAN
S/N | Activity Description | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementation Status | Remarks
|  | IGF | GOG | DONORS | TOTAL
DEPARTMENT OF HUMAN RESOURCE
APPROVED 2020 ANNUAL ACTION PLAN
S/N | Activity Description | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementation Status | Remarks
|  | IGF | GOG | DONORS | TOTAL
1 | Provide 2-day training on LGS Protocols |  | 12000 |  | 12000 | DACF
2 | Train Revenue collectors/ Data billing personnel | 49000 |  |  | 49000 | IGF |  | CONTRACTORS SHOULD BEAR PART OF COST INCURED IN TRAINNING
3 | Train Assembly members on budget and plan preparation, Local Governance System |  | 20000 |  | 20000 | DACF
4 | Organise orientation for 2020-2021 national service personel | 5000 |  |  | 5000 | IGF
5 | Organise training programme for the taskforce of the Assembly |  | 10000 |  | 10000 | DACF |  | DELETE REPALCE WITH STAFF DURBAR
| TOTAL |  |  |  | 96000
DEPARTMENT OF INFORMATION SERVICE
APPROVED 2020 ANNUAL ACTION PLAN
S/N | Activity Description | Estimated Budget (GHS) |  |  |  | Source of Funding | Implementation Status | Remarks
|  | IGF | GOG | DONORS | TOTAL
1 | Organise 4 Town Hall meetings |  | 98000 |  | 98000 | DACF |  | RDUCE TO 2NO.
2 | Organise public education on the functions of the Assembly | 24000 |  |  | 24000 | IGF
| TOTAL |  |  |  | 122000